## Instructions
Student Workbook Instructions | stuwbk 20040615
The student workbook provides automated support for the Personal Software Process course. The workbook includes worksheets for the calculation-intensive forms and analysis charts and tables required for reports R3, R4, and R5.
The workbook includes:
Student - a worksheet for the student background survey
Summary - a worksheet containing PSP Project Plan Summary forms for each assignment, 1A to 8A
SizeEstimate - a worksheet contining a PSP Size Estimating Template for each assignment 3A to 8A
PROBE - a worksheet that automates the PROBE method computations
TimeLog - a worksheet for recording all time log data
DefectLog - a worksheet for recording all defect data
R3 - a worksheet that generates the defect analysis tables for the R3 report
R4 - a worksheet that generates the defect analysis tables for the R4 and R5 report
Pareto - a worksheet that generates pareto distributions of defects by type and by fix time
Defect, Plan, Process, and Quality analysis worksheets that include analyses required for the R4 and R5 reports
General Instructions
1. During the planning phase of an assignment, select the assignment number using the project selector on the Summary worksheet. Calculate and enter data in all the highlighted cells containing ????? in the Plan column of the Summary worksheet for that assignment.
For assignments 3A through 8A the SizeEstimate worksheet and the PROBE worksheet are used to generate size and time estimates. The SizeEstimate worksheet replaces the PSP Size Estimating worksheet. The planned and actual LOC are entered on this form (e.g. Base LOC, Deleted LOC, Modified LOC, Base Additions, New Object LOC, and Reused LOC).
The PROBE worksheet is used to select the estimating method, regression parameters, prediction intervals, and size and time estimates. The estimate is then transferred to the SizeEstimate worksheet.
2. During the development phases, use the time and defect logs to capture actual time and defect data for the assignment, or record this data on paper forms and enter during postmortem.
3. During the postmortem phase of an assignment, calculate and enter data in all the highlighted cells that contain ????? in the Actual, ToDate, or ToDate% columns for the assignment. For assignments 3A to 8A, measure and enter actual LOC on the SizeEstimate worksheet.
4. To print a Summary report, select the assignment with the project selector and print. For assignments 1A to 6A, an extra blank page will be printed. Print page 1 only to avoid printing the blank page.
Application Notes:
A. Only enter data in highlighted fields containing ?????.
B. All other fields contain formulas that are calculated by Excel and are locked to prevent accidental entry.
C. If you need to modify a protected cell you may turn cell protection off.
D. After your modifications are complete turn cell protection back.
E. Excel will request a password when you turn protection on. DO NOT ENTER A PASSWORD.
F.The Summary worksheet automates many of the PSP calculations, but as new PSP measures appear on the worksheet, they must be calculated and entered manually.

## Student
PSP Student Background Survey
|  | Student Name | Student #
Instructor Name(s)
1 |  | Which of the following best describes your employment status in the software industry (mark one with an X) |  | Job Position
Executive
Management
Senior technical
Technical
Full-time support
Other
2 |  | What is your software experience in: (Please specify for each category, rounded to the nearest year) |  | Prog. Experience
YRS.
In your present organization?
In your present position?
Your overall software experience?
Software requirements?
Software design?
Code and unit test?
Test and integration?
Software quality assurance?
Configuration management?
Software process improvement/quality management?
3 |  | About how much of your work-related time have you spent over the past year on each of the following? Please specify an approximate percentage for each, rounded up to the nearest whole number (with no % sign). The categories overlap, so your estimates need not total 100% |  | % S/W Time
Software requirements?
Software design?
Code and unit test?
Test and integration?
Software quality assurance?
Configuration management?
Software process improvement/quality management?
Other
4 |  | What programming languages have you used? (Please mark as many as apply with an X)
Ada
Basic
C
C++
Java
PASCAL
OBJECT PASCAL
Visual Basic
Visual C++
OTHER
4.1 |  | How many high level languages do you know well? (Please specify) |  | Lang#
Number of languages
5 |  | What language will you use in this course? |  | Language
Ada
Basic
C
C++
Java
PASCAL
OBJECT PASCAL
Visual Basic
Visual C++
OTHER
5.1 |  | Approximately how much code have you written in this language? (please specify, rounded to the nearest 1,000 lines of code, e.g. 10K) |  | KLOC - L
Lines of Code
5.2 |  | Approximately how much code have you written in all languages? (please specify, rounded to the nearest 1,000 lines of code, e.g. 10K) |  | KLOC - T
Lines of Code
5.3 |  | Approximately how much code have you written in the last year? (please specify, rounded to the nearest 1,000 lines of code, e.g. 10K) |  | KLOC - Y
Lines of Code - In the language you will be using
Lines of Code - In all languages
6 |  | What is the highest degree that you have attained? (please specify)
|  | Highest degree |  | Highest Degree
6.1 |  | What was your major field of study? (please specify)
6.2 |  | Have you had courses in any of the following subjects? (Please mark all that apply with an X)
|  | Statistics |  | Statistics
|  | Physical Sciences |  | PhyScy
|  | Software Project Management |  | ProjMgt
|  | Formal Software Methods |  | FormMeth
YrsProg

## Summary
[64 empty] | A copy of the data entered in your StuN file. |  |  |  |  | Source: plan summary cells
1 | PSP0 Project Plan Summary - Program 1A | [6 empty] | PSP0.1 Project Plan Summary - Program 2A | [5 empty] | PSP1 Project Plan Summary - Program 3A | [5 empty] | PSP1.1 Project Plan Summary - Program 4A | [5 empty] | PSP2 Project Plan Summary - Program 5A | [5 empty] | PSP2.1 Project Plan Summary - Program 6A | [5 empty] | PSP2.1 Project Plan Summary - Program 7A | [5 empty] | PSP2.1 Project Plan Summary - Program 8A | [5 empty] | PSP2.1 Project Plan Summary - Program 9A | [5 empty] | PSP3 Project Plan Summary - Program 10A | [5 empty] | EstObjLOC | ActObjLOC | Item: | EstLoc | ActLOC | EstMin | ActMin | EstDef | ActDef | Time by Phase | [15 empty] | Defects Injected by Phase | [13 empty] | Defects Removed by Phase
[71 empty] | Planning |  | Design |  | DLDR |  | Code |  | CR |  | Compile |  | Test |  | PM |  | Plng |  | Design |  | DLDR |  | Code |  | CR |  | Compile |  | Test |  | Plng |  | Design |  | DLDR |  | Code |  | CR |  | Compile |  | Test
| Student |  |  |  | Date |  | ????? | Student |  |  |  | Date | ????? | Student |  |  |  | Date | ????? | Student |  |  |  | Date | ????? | Student |  |  |  | Date | ????? | Student |  |  |  | Date | ????? | Student |  |  |  | Date | ????? | Student |  |  |  | Date | ????? | Student |  |  |  | Date | ????? | Student |  |  |  | Date | ????? | [9 empty] | Est | Act | Est | Act | Est | Act | Est | Act | Est | Act | Est | Act | Est | Act | Est | Act | Est | Act | Est | Act | Est | Act | Est | Act | Est | Act | Est | Act | Est | Act | Est | Act | Est | Act | Est | Act | Est | Act | Est | Act | Est | Act | Est | Act
| Program | Correlation |  |  | Program# |  | 1A | Program | LOC Counter |  |  | Program# | 2A | Program | Linear Regression |  |  | Program# | 3A | Program | Numerical Integration |  |  | Program# | 4A | Program | Sort |  |  | Program# | 5A | Program | Prediction Interval |  |  | Program# | 6A | Program | Chi-square Test |  |  | Program# | 7A | Program | Multiple Regression |  |  | Program# | 8A | Program | Chi-square Test |  |  | Program# | 9A | Program | Multiple Regression |  |  | Program# | 10A |  |  | Formulas
| Instructor |  |  |  | Language |  | ????? | Instructor |  |  |  | Language | ????? | Instructor |  |  |  | Language | ????? | Instructor |  |  |  | Language | ????? | Instructor |  |  |  | Language | ????? | Instructor |  |  |  | Language | ????? | Instructor |  |  |  | Language | ????? | Instructor |  |  |  | Language | ????? | Instructor |  |  |  | Language | ????? | Instructor |  |  |  | Language | ????? |  |  | 1 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  | 0
[64 empty] | 2 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  | 0
|  |  | Plan | Actual | To Date |  | To Date% |  |  | Plan | Actual | To Date | To Date% |  |  | Plan | Actual | To Date | To Date% |  |  | Plan | Actual | To Date | To Date% |  |  | Plan | Actual | To Date | To Date% |  |  | Plan | Actual | To Date | To Date% |  |  | Plan | Actual | To Date | To Date% |  |  | Plan | Actual | To Date | To Date% |  |  | Plan | Actual | To Date | To Date% |  |  | Plan | Actual | To Date | To Date% | 0 | 0 | 3 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  | 0
| Time in Phase (min.) | [6 empty] | Program Size (LOC) | [5 empty] | Summary | [5 empty] | Summary | [5 empty] | Summary | [5 empty] | Summary | [5 empty] | Summary | [5 empty] | Summary | [5 empty] | Summary | [5 empty] | Summary | [5 empty] | 0 | 0 | 4 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  | 0
| Planning |  |  | 0 | 0 |  | 0 | Base(B) |  |  | ????? |  |  | LOC/Hour |  | ????? | ????? | ????? |  | LOC/Hour |  | 0 | 0 | 0 |  | LOC/Hour |  | 0 | 0 | 0 |  | LOC/Hour |  | 0 | 0 | 0 |  | LOC/Hour |  | 0 | 0 | 0 |  | LOC/Hour |  | 0 | 0 | 0 |  | LOC/Hour |  | 0 | 0 | 0 |  | LOC/Hour |  | 0 | 0 | 0 |  | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Design |  |  | 0 | 0 |  | 0 | Deleted(D) |  |  | ????? | [8 empty] | Planned Time |  | 0 |  | ????? |  | Planned Time |  | 0 |  | 0 |  | Planned Time |  | 0 |  | 0 |  | Planned Time |  | 0 |  | 0 |  | Planned Time |  | 0 |  | 0 |  | Planned Time |  | 0 |  | 0 |  | Planned Time |  | 0 |  | 0 |  | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Code |  |  | 0 | 0 |  | 0 | Modified(M) |  |  | ????? |  |  | Program Size (LOC) | [5 empty] | Actual Time |  |  | 0 | ????? |  | Actual Time |  |  | 0 | 0 |  | Actual Time |  |  | 0 | 0 |  | Actual Time |  |  | 0 | 0 |  | Actual Time |  |  | 0 | 0 |  | Actual Time |  |  | 0 | 0 |  | Actual Time |  |  | 0 | 0 |  | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Compile |  |  | 0 | 0 |  | 0 | Added(A) |  |  | ????? |  |  | Base(B) |  | 0 | 0 |  |  | CPI (Planned/Actual Time) |  |  |  | ????? |  | CPI (Planned/Actual Time) |  |  |  | 0 |  | CPI (Planned/Actual Time) |  |  |  | 0 |  | CPI (Planned/Actual Time) |  |  |  | 0 |  | CPI (Planned/Actual Time) |  |  |  | 0 |  | CPI (Planned/Actual Time) |  |  |  | 0 |  | CPI (Planned/Actual Time) |  |  |  | 0 |  | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Test |  |  | 0 | 0 |  | 0 | Reused(R) |  |  | ????? | ????? |  | Deleted(D) |  | 0 | 0 |  |  | % Reused |  | ????? | ????? | ????? |  | % Reused |  | 0 | 0 | 0 |  | % Reused |  | 0 | 0 | 0 |  | % Reused |  | 0 | 0 | 0 |  | % Reused |  | 0 | 0 | 0 |  | % Reused |  | 0 | 0 | 0 |  | % Reused |  | 0 | 0 | 0 |  | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Postmortem |  |  | 0 | 0 |  | 0 | Total N&C (N) |  | ????? | ????? | ????? |  | Modified(M) |  | 0 | 0 |  |  | % New Reused |  | ????? | ????? | ????? |  | % New Reused |  | 0 | 0 | 0 |  | % New Reused |  | 0 | 0 | 0 |  | % New Reused |  | 0 | 0 | 0 |  | % New Reused |  | 0 | 0 | 0 |  | % New Reused |  | 0 | 0 | 0 |  | % New Reused |  | 0 | 0 | 0 |  | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total |  | ????? | 0 | 0 | 0 | 0 | Total LOC(T) |  |  | ????? | ????? |  | Added(A) |  | 0 | 0 | [8 empty] | Test Defects/KLOC |  | ????? | ????? | ????? |  | Test Defects/KLOC |  | 0 | 0 | 0 |  | Test Defects/KLOC |  | 0 | 0 | 0 |  | Test Defects/KLOC |  | 0 | 0 | 0 |  | Test Defects/KLOC |  | 0 | 0 | 0 |  | Test Defects/KLOC |  | 0 | 0 | 0 |  | 0 | 0 | Totals | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | Total New Reused |  |  | ????? | ????? |  | Reused(R) |  | 0 | 0 | 0 |  | Program Size (LOC) | [5 empty] | Total Defects/KLOC |  | ????? | ????? | ????? |  | Total Defects/KLOC |  | 0 | 0 | 0 |  | Total Defects/KLOC |  | 0 | 0 | 0 |  | Total Defects/KLOC |  | 0 | 0 | 0 |  | Total Defects/KLOC |  | 0 | 0 | 0 |  | Total Defects/KLOC |  | 0 | 0 | 0
| Defects Injected | [12 empty] | Total N&C (N) |  | 0 | 0 | 0 |  | Base(B) |  | 0 | 0 |  |  | Yield % |  | ????? | ????? | ????? |  | Yield % |  | 100 | 100 | 100 |  | Yield % |  | 100 | 100 | 100 |  | Yield % |  | 100 | 100 | 100 |  | Yield % |  | 100 | 100 | 100 |  | Yield % |  | 100 | 100 | 100
| Planning |  |  | 0 | 0 |  | 0 | Time in Phase (min.) | [5 empty] | Total LOC(T) |  | 0 | ????? | 0 |  | Deleted(D) |  | 0 | 0 | [8 empty] | % Appraisal COQ |  | ????? | ????? | ????? |  | % Appraisal COQ |  | 0 | 0 | 0 |  | % Appraisal COQ |  | 0 | 0 | 0 |  | % Appraisal COQ |  | 0 | 0 | 0 |  | % Appraisal COQ |  | 0 | 0 | 0
| Design |  |  | 0 | 0 |  | 0 | Planning |  | ????? | 0 | 0 | 0 | Total New Reused |  | 0 | 0 | 0 |  | Modified(M) |  | 0 | 0 |  |  | Program Size (LOC) | [5 empty] | % Failure COQ |  | ????? | ????? | ????? |  | % Failure COQ |  | 0 | 0 | 0 |  | % Failure COQ |  | 0 | 0 | 0 |  | % Failure COQ |  | 0 | 0 | 0 |  | % Failure COQ |  | 0 | 0 | 0
| Code |  |  | 0 | 0 |  | 0 | Design |  | ????? | 0 | 0 | 0 | Total Object LOC(E) |  | 0 | 0 | 0 |  | Added(A) |  | 0 | 0 |  |  | Base(B) |  | 0 | 0 |  |  | COQ A/F Ratio |  | ????? | ????? | ????? |  | COQ A/F Ratio |  | 0 | 0 | 0 |  | COQ A/F Ratio |  | 0 | 0 | 0 |  | COQ A/F Ratio |  | 0 | 0 | 0 |  | COQ A/F Ratio |  | 0 | 0 | 0
| Compile |  |  | 0 | 0 |  | 0 | Code |  | ????? | 0 | 0 | 0 | [6 empty] | Reused(R) |  | 0 | 0 | 0 |  | Deleted(D) |  | 0 | 0
| Test |  |  | 0 | 0 |  | 0 | Compile |  | ????? | 0 | 0 | 0 | Time in Phase (min.) | [5 empty] | Total N&C (N) |  | 0 | 0 | 0 |  | Modified(M) |  | 0 | 0 |  |  | Program Size (LOC) | [5 empty] | Program Size (LOC) | [5 empty] | Program Size (LOC) | [5 empty] | Program Size (LOC) | [5 empty] | Program Size (LOC)
| Total Development |  |  | 0 | 0 | 0 | 0 | Test |  | ????? | 0 | 0 | 0 | Planning |  | 0 | 0 | 0 | 0 | Total LOC(T) |  | 0 | ????? | 0 |  | Added(A) |  | 0 | 0 |  |  | Base(B) |  | 0 | 0 |  |  | Base(B) |  | 0 | 0 |  |  | Base(B) |  | 0 | 0 |  |  | Base(B) |  | 0 | 0 |  |  | Base(B) |  | 0 | 0
[8 empty] | Postmortem |  | ????? | 0 | 0 | 0 | Design |  | 0 | 0 | 0 | 0 | Total New Reused |  | 0 | 0 | 0 |  | Reused(R) |  | 0 | 0 | 0 |  | Deleted(D) |  | 0 | 0 |  |  | Deleted(D) |  | 0 | 0 |  |  | Deleted(D) |  | 0 | 0 |  |  | Deleted(D) |  | 0 | 0 |  |  | Deleted(D) |  | 0 | 0
| Defects Removed | [6 empty] | Total |  | ????? | 0 | 0 | 0 | Code |  | 0 | 0 | 0 | 0 | Total Object LOC(E) |  | 0 | 0 | 0 |  | Total N&C (N) |  | 0 | 0 | 0 |  | Modified(M) |  | 0 | 0 |  |  | Modified(M) |  | 0 | 0 |  |  | Modified(M) |  | 0 | 0 |  |  | Modified(M) |  | 0 | 0 |  |  | Modified(M) |  | 0 | 0
| Planning |  |  | 0 | 0 |  | 0 | [6 empty] | Compile |  | 0 | 0 | 0 | 0 | [6 empty] | Total LOC(T) |  | 0 | ????? | 0 |  | Added(A) |  | 0 | 0 |  |  | Added(A) |  | 0 | 0 |  |  | Added(A) |  | 0 | 0 |  |  | Added(A) |  | 0 | 0 |  |  | Added(A) |  | 0 | 0
| Design |  |  | 0 | 0 |  | 0 | Defects Injected | [5 empty] | Test |  | 0 | 0 | 0 | 0 | Time in Phase (min.) | [5 empty] | Total New Reused |  | 0 | 0 | 0 |  | Reused(R) |  | 0 | 0 | 0 |  | Reused(R) |  | 0 | 0 | 0 |  | Reused(R) |  | 0 | 0 | 0 |  | Reused(R) |  | 0 | 0 | 0 |  | Reused(R) |  | 0 | 0 | 0
| Code |  |  | 0 | 0 |  | 0 | Planning |  |  | 0 | 0 | 0 | Postmortem |  | 0 | 0 | 0 | 0 | Planning |  | 0 | 0 | 0 | 0 | Total Object LOC(E) |  | 0 | 0 | 0 |  | Total N&C (N) |  | 0 | 0 | 0 |  | Total N&C (N) |  | 0 | 0 | 0 |  | Total N&C (N) |  | 0 | 0 | 0 |  | Total N&C (N) |  | 0 | 0 | 0 |  | Total N&C (N) |  | 0 | 0 | 0
| Compile |  |  | 0 | 0 |  | 0 | Design |  |  | 0 | 0 | 0 | Total |  | 0 | 0 | 0 | 0 | Design |  | 0 | 0 | 0 | 0 | UPI (70%) | [5 empty] | Total LOC(T) |  | 0 | ????? | 0 |  | Total LOC(T) |  | 0 | ????? | 0 |  | Total LOC(T) |  | 0 | ????? | 0 |  | Total LOC(T) |  | 0 | ????? | 0 |  | Total LOC(T) |  | 0 | ????? | 0
| Test |  |  | 0 | 0 |  | 0 | Code |  |  | 0 | 0 | 0 | [6 empty] | Code |  | 0 | 0 | 0 | 0 | LPI (70%) | [5 empty] | Total New Reused |  | 0 | 0 | 0 |  | Total New Reused |  | 0 | 0 | 0 |  | Total New Reused |  | 0 | 0 | 0 |  | Total New Reused |  | 0 | 0 | 0 |  | Total New Reused |  | 0 | 0 | 0
| Total Development |  |  | 0 | 0 | 0 | 0 | Compile |  |  | 0 | 0 | 0 | Defects Injected | [5 empty] | Compile |  | 0 | 0 | 0 | 0 | [6 empty] | Total Object LOC(E) |  | 0 | 0 | 0 |  | Total Object LOC(E) |  | 0 | 0 | 0 |  | Total Object LOC(E) |  | 0 | 0 | 0 |  | Total Object LOC(E) |  | 0 | 0 | 0 |  | Total Object LOC(E) |  | 0 | 0 | 0
| After Development |  |  | ????? | ????? |  |  | Test |  |  | 0 | 0 | 0 | Planning |  |  | 0 | 0 | 0 | Test |  | 0 | 0 | 0 | 0 | Time in Phase (min.) | [5 empty] | UPI (70%) | [5 empty] | UPI (70%) | [5 empty] | UPI (70%) | [5 empty] | UPI (70%) | [5 empty] | UPI (70%)
[8 empty] | Total Development |  |  | 0 | 0 | 0 | Design |  |  | 0 | 0 | 0 | Postmortem |  | 0 | 0 | 0 | 0 | Planning |  | ????? | 0 | 0 | 0 | LPI (70%) | [5 empty] | LPI (70%) | [5 empty] | LPI (70%) | [5 empty] | LPI (70%) | [5 empty] | LPI (70%)
[14 empty] | Code |  |  | 0 | 0 | 0 | Total |  | 0 | 0 | 0 | 0 | Design |  | ????? | 0 | 0 | 0
[8 empty] | Defects Removed | [5 empty] | Compile |  |  | 0 | 0 | 0 | [6 empty] | Design Review |  | ????? | 0 | 0 | 0 | Time in Phase (min.) | [5 empty] | Time in Phase (min.) | [5 empty] | Time in Phase (min.) | [5 empty] | Time in Phase (min.) | [5 empty] | Time in Phase (min.)
[8 empty] | Planning |  |  | 0 | 0 | 0 | Test |  |  | 0 | 0 | 0 | Defects Injected | [5 empty] | Code |  | ????? | 0 | 0 | 0 | Planning |  | 0 | 0 | 0 | 0 | Planning |  | 0 | 0 | 0 | 0 | Planning |  | 0 | 0 | 0 | 0 | Planning |  | 0 | 0 | 0 | 0 | Planning |  | 0 | 0 | 0 | 0
[8 empty] | Design |  |  | 0 | 0 | 0 | Total Development |  |  | 0 | 0 | 0 | Planning |  |  | 0 | 0 | 0 | Code Review |  | ????? | 0 | 0 | 0 | Design |  | 0 | 0 | 0 | 0 | Design |  | 0 | 0 | 0 | 0 | Design |  | 0 | 0 | 0 | 0 | Design |  | 0 | 0 | 0 | 0 | High-level Design |  | 0 | 0 | 0 | 0
[8 empty] | Code |  |  | 0 | 0 | 0 | [6 empty] | Design |  |  | 0 | 0 | 0 | Compile |  | ????? | 0 | 0 | 0 | Design Review |  | 0 | 0 | 0 | 0 | Design Review |  | 0 | 0 | 0 | 0 | Design Review |  | 0 | 0 | 0 | 0 | Design Review |  | 0 | 0 | 0 | 0 | HLDR |  | 0 | 0 | 0 | 0
[8 empty] | Compile |  |  | 0 | 0 | 0 | Defects Removed | [5 empty] | Code |  |  | 0 | 0 | 0 | Test |  | ????? | 0 | 0 | 0 | Code |  | 0 | 0 | 0 | 0 | Code |  | 0 | 0 | 0 | 0 | Code |  | 0 | 0 | 0 | 0 | Code |  | 0 | 0 | 0 | 0 | Design |  | 0 | 0 | 0 | 0
[8 empty] | Test |  |  | 0 | 0 | 0 | Planning |  |  | 0 | 0 | 0 | Compile |  |  | 0 | 0 | 0 | Postmortem |  | ????? | 0 | 0 | 0 | Code Review |  | 0 | 0 | 0 | 0 | Code Review |  | 0 | 0 | 0 | 0 | Code Review |  | 0 | 0 | 0 | 0 | Code Review |  | 0 | 0 | 0 | 0 | Design Review |  | 0 | 0 | 0 | 0
[8 empty] | Total Development |  |  | 0 | 0 | 0 | Design |  |  | 0 | 0 | 0 | Test |  |  | 0 | 0 | 0 | Total |  | ????? | 0 | 0 | 0 | Compile |  | 0 | 0 | 0 | 0 | Compile |  | 0 | 0 | 0 | 0 | Compile |  | 0 | 0 | 0 | 0 | Compile |  | 0 | 0 | 0 | 0 | Code |  | 0 | 0 | 0 | 0
[8 empty] | After Development |  |  | ????? | ????? |  | Code |  |  | 0 | 0 | 0 | Total Development |  |  | 0 | 0 | 0 | UPI (70%) |  | ????? |  |  |  | Test |  | 0 | 0 | 0 | 0 | Test |  | 0 | 0 | 0 | 0 | Test |  | 0 | 0 | 0 | 0 | Test |  | 0 | 0 | 0 | 0 | Code Review |  | 0 | 0 | 0 | 0
[14 empty] | Compile |  |  | 0 | 0 | 0 | [6 empty] | LPI (70%) |  | ????? |  |  |  | Postmortem |  | 0 | 0 | 0 | 0 | Postmortem |  | 0 | 0 | 0 | 0 | Postmortem |  | 0 | 0 | 0 | 0 | Postmortem |  | 0 | 0 | 0 | 0 | Compile |  | 0 | 0 | 0 | 0
[14 empty] | Test |  |  | 0 | 0 | 0 | Defects Removed | [11 empty] | Total |  | 0 | 0 | 0 | 0 | Total |  | 0 | 0 | 0 | 0 | Total |  | 0 | 0 | 0 | 0 | Total |  | 0 | 0 | 0 | 0 | Test |  | 0 | 0 | 0 | 0
[14 empty] | Total Development |  |  | 0 | 0 | 0 | Planning |  |  | 0 | 0 | 0 | [6 empty] | UPI (70%) | [5 empty] | UPI (70%) | [5 empty] | UPI (70%) | [5 empty] | UPI (70%) | [5 empty] | Postmortem |  | 0 | 0 | 0 | 0
[14 empty] | After Development |  |  | ????? | ????? |  | Design |  |  | 0 | 0 | 0 | [6 empty] | LPI (70%) | [5 empty] | LPI (70%) | [5 empty] | LPI (70%) | [5 empty] | LPI (70%) | [5 empty] | Total |  | 0 | 0 | 0 | 0
[20 empty] | Code |  |  | 0 | 0 | 0 | [30 empty] | UPI (70%)
[20 empty] | Compile |  |  | 0 | 0 | 0 | [30 empty] | LPI (70%)
[20 empty] | Test |  |  | 0 | 0 | 0
[20 empty] | Total Development |  |  | 0 | 0 | 0
[20 empty] | After Development |  |  | ????? | ?????
[26 empty] | PSP2 Project Plan Summary - Program 5A (Continued) | [5 empty] | PSP2.1 Project Plan Summary - Program 6A (Continued) | [5 empty] | PSP2.1 Project Plan Summary - Program 7A (Continued) | [5 empty] | PSP2.1 Project Plan Summary - Program 8A (Continued) | [5 empty] | PSP2.1 Project Plan Summary - Program 9A (Continued) | [5 empty] | PSP3 Project Plan Summary - Program 10A (Continued)
[26 empty] | Student |  |  |  | Date | ????? | Student |  |  |  | Date | ????? | Student |  |  |  | Date | ????? | Student |  |  |  | Date | ????? | Student |  |  |  | Date | ????? | Student |  |  |  | Date | ?????
[26 empty] | Program | Sort |  |  | Program# | 5A | Program | Prediction Interval |  |  | Program# | 6A | Program | Chi-square Test |  |  | Program# | 7A | Program | List Sort |  |  | Program# | 8A | Program | Chi-square Test |  |  | Program# | 9A | Program | Multiple Regression |  |  | Program# | 10A
[26 empty] | Instructor |  |  |  | Language | ????? | Instructor |  |  |  | Language | ????? | Instructor |  |  |  | Language | ????? | Instructor |  |  |  | Language | ????? | Instructor |  |  |  | Language | ????? | Instructor |  |  |  | Language | ?????
[28 empty] | Plan | Actual | To Date | To Date% |  |  | Plan | Actual | To Date | To Date% |  |  | Plan | Actual | To Date | To Date% |  |  | Plan | Actual | To Date | To Date% |  |  | Plan | Actual | To Date | To Date% |  |  | Plan | Actual | To Date | To Date%
[26 empty] | Defects Injected | [5 empty] | Defects Injected | [5 empty] | Defects Injected | [5 empty] | Defects Injected | [5 empty] | Defects Injected | [5 empty] | Defects Injected
[26 empty] | Planning |  | ????? | 0 | 0 | 0 | Planning |  | 0 | 0 | 0 | 0 | Planning |  | 0 | 0 | 0 | 0 | Planning |  | 0 | 0 | 0 | 0 | Planning |  | 0 | 0 | 0 | 0 | Planning |  | 0 | 0 | 0 | 0
[26 empty] | Design |  | ????? | 0 | 0 | 0 | Design |  | 0 | 0 | 0 | 0 | Design |  | 0 | 0 | 0 | 0 | Design |  | 0 | 0 | 0 | 0 | Design |  | 0 | 0 | 0 | 0 | High-level Design |  | 0 | 0 | 0 | 0
[26 empty] | Design Review |  | ????? | 0 | 0 | 0 | Design Review |  | 0 | 0 | 0 | 0 | Design Review |  | 0 | 0 | 0 | 0 | Design Review |  | 0 | 0 | 0 | 0 | Design Review |  | 0 | 0 | 0 | 0 | HLDR |  | 0 | 0 | 0 | 0
[26 empty] | Code |  | ????? | 0 | 0 | 0 | Code |  | 0 | 0 | 0 | 0 | Code |  | 0 | 0 | 0 | 0 | Code |  | 0 | 0 | 0 | 0 | Code |  | 0 | 0 | 0 | 0 | Design |  | 0 | 0 | 0 | 0
[26 empty] | Code Review |  | ????? | 0 | 0 | 0 | Code Review |  | 0 | 0 | 0 | 0 | Code Review |  | 0 | 0 | 0 | 0 | Code Review |  | 0 | 0 | 0 | 0 | Code Review |  | 0 | 0 | 0 | 0 | Design Review |  | 0 | 0 | 0 | 0
[26 empty] | Compile |  | ????? | 0 | 0 | 0 | Compile |  | 0 | 0 | 0 | 0 | Compile |  | 0 | 0 | 0 | 0 | Compile |  | 0 | 0 | 0 | 0 | Compile |  | 0 | 0 | 0 | 0 | Code |  | 0 | 0 | 0 | 0
[26 empty] | Test |  | ????? | 0 | 0 | 0 | Test |  | 0 | 0 | 0 | 0 | Test |  | 0 | 0 | 0 | 0 | Test |  | 0 | 0 | 0 | 0 | Test |  | 0 | 0 | 0 | 0 | Code Review |  | 0 | 0 | 0 | 0
[26 empty] | Total Development |  | ????? | 0 | 0 | 0 | Total Development |  | 0 | 0 | 0 | 0 | Total Development |  | 0 | 0 | 0 | 0 | Total Development |  | 0 | 0 | 0 | 0 | Total Development |  | 0 | 0 | 0 | 0 | Compile |  | 0 | 0 | 0 | 0
[56 empty] | Test |  | 0 | 0 | 0 | 0
[26 empty] | Defects Removed | [5 empty] | Defects Removed | [5 empty] | Defects Removed | [5 empty] | Defects Removed | [5 empty] | Defects Removed | [5 empty] | Total Development |  | 0 | 0 | 0 | 0
[26 empty] | Planning |  | ????? | 0 | 0 | 0 | Planning |  | 0 | 0 | 0 | 0 | Planning |  | 0 | 0 | 0 | 0 | Planning |  | 0 | 0 | 0 | 0 | Planning |  | 0 | 0 | 0 | 0
[26 empty] | Design |  | ????? | 0 | 0 | 0 | Design |  | 0 | 0 | 0 | 0 | Design |  | 0 | 0 | 0 | 0 | Design |  | 0 | 0 | 0 | 0 | Design |  | 0 | 0 | 0 | 0 | Defects Removed
[26 empty] | Design Review |  | ????? | 0 | 0 | 0 | Design Review |  | 0 | 0 | 0 | 0 | Design Review |  | 0 | 0 | 0 | 0 | Design Review |  | 0 | 0 | 0 | 0 | Design Review |  | 0 | 0 | 0 | 0 | Planning |  | 0 | 0 | 0 | 0
[26 empty] | Code |  | ????? | 0 | 0 | 0 | Code |  | 0 | 0 | 0 | 0 | Code |  | 0 | 0 | 0 | 0 | Code |  | 0 | 0 | 0 | 0 | Code |  | 0 | 0 | 0 | 0 | High-level Design |  | 0 | 0 | 0 | 0
[26 empty] | Code Review |  | ????? | 0 | 0 | 0 | Code Review |  | 0 | 0 | 0 | 0 | Code Review |  | 0 | 0 | 0 | 0 | Code Review |  | 0 | 0 | 0 | 0 | Code Review |  | 0 | 0 | 0 | 0 | HLDR |  | 0 | 0 | 0 | 0
[26 empty] | Compile |  | ????? | 0 | 0 | 0 | Compile |  | 0 | 0 | 0 | 0 | Compile |  | 0 | 0 | 0 | 0 | Compile |  | 0 | 0 | 0 | 0 | Compile |  | 0 | 0 | 0 | 0 | Design |  | 0 | 0 | 0 | 0
[26 empty] | Test |  | ????? | 0 | 0 | 0 | Test |  | 0 | 0 | 0 | 0 | Test |  | 0 | 0 | 0 | 0 | Test |  | 0 | 0 | 0 | 0 | Test |  | 0 | 0 | 0 | 0 | Design Review |  | 0 | 0 | 0 | 0
[26 empty] | Total Development |  | ????? | 0 | 0 | 0 | Total Development |  | 0 | 0 | 0 | 0 | Total Development |  | 0 | 0 | 0 | 0 | Total Development |  | 0 | 0 | 0 | 0 | Total Development |  | 0 | 0 | 0 | 0 | Code |  | 0 | 0 | 0 | 0
[26 empty] | After Development |  |  | ????? | ????? |  | After Development |  |  | ????? | ????? |  | After Development |  |  | ????? | ????? |  | After Development |  |  | ????? | ????? |  | After Development |  |  | ????? | ????? |  | Code Review |  | 0 | 0 | 0 | 0
[56 empty] | Compile |  | 0 | 0 | 0 | 0
[26 empty] | Defect Removal Efficiency | [5 empty] | Defect Removal Efficiency | [5 empty] | Defect Removal Efficiency | [5 empty] | Defect Removal Efficiency | [5 empty] | Defect Removal Efficiency | [5 empty] | Test |  | 0 | 0 | 0 | 0
[26 empty] | Def/Hr - DLDR |  | ????? | ????? | ????? |  | Def/Hr - DLDR |  | 0 | 0 | 0 |  | Def/Hr - DLDR |  | 0 | 0 | 0 |  | Def/Hr - DLDR |  | 0 | 0 | 0 |  | Def/Hr - DLDR |  | 0 | 0 | 0 |  | Total Development |  | 0 | 0 | 0 | 0
[26 empty] | Def/Hr - CDR |  | ????? | ????? | ????? |  | Def/Hr - CDR |  | 0 | 0 | 0 |  | Def/Hr - CDR |  | 0 | 0 | 0 |  | Def/Hr - CDR |  | 0 | 0 | 0 |  | Def/Hr - CDR |  | 0 | 0 | 0 |  | After Development |  |  | ????? | ?????
[26 empty] | Def/Hr - Compile |  | ????? | ????? | ????? |  | Def/Hr - Compile |  | 0 | 0 | 0 |  | Def/Hr - Compile |  | 0 | 0 | 0 |  | Def/Hr - Compile |  | 0 | 0 | 0 |  | Def/Hr - Compile |  | 0 | 0 | 0
[26 empty] | Def/Hr - Test |  | ????? | ????? | ????? |  | Def/Hr - Test |  | 0 | 0 | 0 |  | Def/Hr - Test |  | 0 | 0 | 0 |  | Def/Hr - Test |  | 0 | 0 | 0 |  | Def/Hr - Test |  | 0 | 0 | 0 |  | Defect Removal Efficiency
[26 empty] | DRL(DLDR/UT) |  | ????? | ????? | ????? |  | DRL(DLDR/UT) |  | 0 | 0 | 0 |  | DRL(DLDR/UT) |  | 0 | 0 | 0 |  | DRL(DLDR/UT) |  | 0 | 0 | 0 |  | DRL(DLDR/UT) |  | 0 | 0 | 0 |  | Def/Hr - HLDR |  | 0 | 0 | 0
[26 empty] | DRL(CDR/UT) |  | ????? | ????? | ????? |  | DRL(CDR/UT) |  | 0 | 0 | 0 |  | DRL(CDR/UT) |  | 0 | 0 | 0 |  | DRL(CDR/UT) |  | 0 | 0 | 0 |  | DRL(CDR/UT) |  | 0 | 0 | 0 |  | Def/Hr - DLDR |  | 0 | 0 | 0
[26 empty] | DRL(Compile/UT) |  | ????? | ????? | ????? |  | DRL(Compile/UT) |  | 0 | 0 | 0 |  | DRL(Compile/UT) |  | 0 | 0 | 0 |  | DRL(Compile/UT) |  | 0 | 0 | 0 |  | DRL(Compile/UT) |  | 0 | 0 | 0 |  | Def/Hr - CDR |  | 0 | 0 | 0
[56 empty] | Def/Hr - Compile |  | 0 | 0 | 0
[56 empty] | Def/Hr - Test |  | 0 | 0 | 0
[56 empty] | DRL(HLDR/UT) |  | 0 | 0 | 0
[56 empty] | DRL(DLDR/UT) |  | 0 | 0 | 0
[56 empty] | DRL(CDR/UT) |  | 0 | 0 | 0
[56 empty] | DRL(Compile/UT) |  | 0 | 0 | 0
Project
Import

## SizeEstimate
1 | Size Estimating Template | [8 empty] | Size Estimating Template | [8 empty] | Size Estimating Template | [8 empty] | Size Estimating Template | [8 empty] | Size Estimating Template | [8 empty] | Size Estimating Template | [8 empty] | Size Estimating Template
| Student | 0 |  |  |  | Date |  | ????? |  | Student | 0 |  |  |  | Date |  | ????? |  | Student | 0 |  |  |  | Date |  | ????? |  | Student | 0 |  |  |  | Date |  | ????? |  | Student | 0 |  |  |  | Date |  | ????? |  | Student | 0 |  |  |  | Date |  | ????? |  | Student | 0 |  |  |  | Date |  | ?????
| Instructor | 0 |  |  |  | Program# |  | 3A |  | Instructor | 0 |  |  |  | Program# |  | 4A |  | Instructor | 0 |  |  |  | Program# |  | 5A |  | Instructor | 0 |  |  |  | Program# |  | 6A |  | Instructor | 0 |  |  |  | Program# |  | 7A |  | Instructor | 0 |  |  |  | Program# |  | 8A |  | Instructor | 0 |  |  |  | Program# |  | 10A
| BASE PROGRAM LOC |  |  |  |  | ESTIMATE |  | ACTUAL |  | BASE PROGRAM LOC |  |  |  |  | ESTIMATE |  | ACTUAL |  | BASE PROGRAM LOC |  |  |  |  | ESTIMATE |  | ACTUAL |  | BASE PROGRAM LOC |  |  |  |  | ESTIMATE |  | ACTUAL |  | BASE PROGRAM LOC |  |  |  |  | ESTIMATE |  | ACTUAL |  | BASE PROGRAM LOC |  |  |  |  | ESTIMATE |  | ACTUAL |  | BASE PROGRAM LOC |  |  |  |  | ESTIMATE |  | ACTUAL
| BASE SIZE (B) => | [8 empty] | BASE SIZE (B) => | [8 empty] | BASE SIZE (B) => | [8 empty] | BASE SIZE (B) => | [8 empty] | BASE SIZE (B) => | [8 empty] | BASE SIZE (B) => | [8 empty] | BASE SIZE (B) =>
| LOC DELETED (D) => | [8 empty] | LOC DELETED (D) => | [8 empty] | LOC DELETED (D) => | [8 empty] | LOC DELETED (D) => | [8 empty] | LOC DELETED (D) => | [8 empty] | LOC DELETED (D) => | [8 empty] | LOC DELETED (D) =>
| LOC MODIFIED (M) => | [8 empty] | LOC MODIFIED (M) => | [8 empty] | LOC MODIFIED (M) => | [8 empty] | LOC MODIFIED (M) => | [8 empty] | LOC MODIFIED (M) => | [8 empty] | LOC MODIFIED (M) => | [8 empty] | LOC MODIFIED (M) =>
| OBJECT LOC | [8 empty] | OBJECT LOC | [8 empty] | OBJECT LOC | [8 empty] | OBJECT LOC | [8 empty] | OBJECT LOC | [8 empty] | OBJECT LOC | [8 empty] | OBJECT LOC
| BASE ADDITIONS: |  | TYPE | METHODS | REL. SIZE | LOC |  | LOC |  | BASE ADDITIONS: |  | TYPE | METHODS | REL. SIZE | LOC |  | LOC |  | BASE ADDITIONS: |  | TYPE | METHODS | REL. SIZE | LOC |  | LOC |  | BASE ADDITIONS: |  | TYPE | METHODS | REL. SIZE | LOC |  | LOC |  | BASE ADDITIONS: |  | TYPE | METHODS | REL. SIZE | LOC |  | LOC |  | BASE ADDITIONS: |  | TYPE | METHODS | REL. SIZE | LOC |  | LOC |  | BASE ADDITIONS: |  | TYPE | METHODS | REL. SIZE | LOC |  | LOC
C++ Object Size in LOC per Method
[64 empty] | Category | VS | S | M | L | VL
[64 empty] | Calc | 2.34 | 5.13 | 11.25 | 24.66 | 54.04
[64 empty] | Data | 2.6 | 4.79 | 8.84 | 16.31 | 30.09
[64 empty] | I/O | 9.01 | 12.06 | 16.15 | 21.62 | 28.93
| (BA) subtotal from page 2 |  |  |  |  | 0 |  | 0 |  | (BA) subtotal from page 2 |  |  |  |  | 0 |  | 0 |  | (BA) subtotal from page 2 |  |  |  |  | 0 |  | 0 |  | (BA) subtotal from page 2 |  |  |  |  | 0 |  | 0 |  | (BA) subtotal from page 2 |  |  |  |  | 0 |  | 0 |  | (BA) subtotal from page 2 |  |  |  |  | 0 |  | 0 |  | (BA) subtotal from page 2 |  |  |  |  | 0 |  | 0 |  | Logic | 7.55 | 10.98 | 15.98 | 23.25 | 33.83
| TOTAL BASE ADDITIONS (BA) |  |  |  |  | 0 |  | 0 |  | TOTAL BASE ADDITIONS (BA) |  |  |  |  | 0 |  | 0 |  | TOTAL BASE ADDITIONS (BA) |  |  |  |  | 0 |  | 0 |  | TOTAL BASE ADDITIONS (BA) |  |  |  |  | 0 |  | 0 |  | TOTAL BASE ADDITIONS (BA) |  |  |  |  | 0 |  | 0 |  | TOTAL BASE ADDITIONS (BA) |  |  |  |  | 0 |  | 0 |  | TOTAL BASE ADDITIONS (BA) |  |  |  |  | 0 |  | 0 |  | Set-up | 3.88 | 5.04 | 6.56 | 8.53 | 11.09
| NEW OBJECTS: |  | TYPE | METHODS | REL. SIZE | LOC | * | LOC | * | NEW OBJECTS: |  | TYPE | METHODS | REL. SIZE | LOC | * | LOC | * | NEW OBJECTS: |  | TYPE | METHODS | REL. SIZE | LOC | * | LOC | * | NEW OBJECTS: |  | TYPE | METHODS | REL. SIZE | LOC | * | LOC | * | NEW OBJECTS: |  | TYPE | METHODS | REL. SIZE | LOC | * | LOC | * | NEW OBJECTS: |  | TYPE | METHODS | REL. SIZE | LOC | * | LOC | * | NEW OBJECTS: |  | TYPE | METHODS | REL. SIZE | LOC | * | LOC | * | Text | 3.75 | 8 | 17.07 | 36.41 | 77.66
| (NO) subtotal from page 2 |  |  |  |  | 0 |  | 0 |  | (NO) subtotal from page 2 |  |  |  |  | 0 |  | 0 |  | (NO) subtotal from page 2 |  |  |  |  | 0 |  | 0 |  | (NO) subtotal from page 2 |  |  |  |  | 0 |  | 0 |  | (NO) subtotal from page 2 |  |  |  |  | 0 |  | 0 |  | (NO) subtotal from page 2 |  |  |  |  | 0 |  | 0 |  | (NO) subtotal from page 2 |  |  |  |  | 0 |  | 0
| TOTAL NEW OBJECTS (NO) |  |  |  |  | 0 |  | 0 |  | TOTAL NEW OBJECTS (NO) |  |  |  |  | 0 |  | 0 |  | TOTAL NEW OBJECTS (NO) |  |  |  |  | 0 |  | 0 |  | TOTAL NEW OBJECTS (NO) |  |  |  |  | 0 |  | 0 |  | TOTAL NEW OBJECTS (NO) |  |  |  |  | 0 |  | 0 |  | TOTAL NEW OBJECTS (NO) |  |  |  |  | 0 |  | 0 |  | TOTAL NEW OBJECTS (NO) |  |  |  |  | 0 |  | 0
| REUSED OBJECTS |  |  |  |  | LOC |  | LOC |  | REUSED OBJECTS |  |  |  |  | LOC |  | LOC |  | REUSED OBJECTS |  |  |  |  | LOC |  | LOC |  | REUSED OBJECTS |  |  |  |  | LOC |  | LOC |  | REUSED OBJECTS |  |  |  |  | LOC |  | LOC |  | REUSED OBJECTS |  |  |  |  | LOC |  | LOC |  | REUSED OBJECTS |  |  |  |  | LOC |  | LOC
| (R) subtotal from page 2 |  |  |  |  | 0 |  | 0 |  | (R) subtotal from page 2 |  |  |  |  | 0 |  | 0 |  | (R) subtotal from page 2 |  |  |  |  | 0 |  | 0 |  | (R) subtotal from page 2 |  |  |  |  | 0 |  | 0 |  | (R) subtotal from page 2 |  |  |  |  | 0 |  | 0 |  | (R) subtotal from page 2 |  |  |  |  | 0 |  | 0 |  | (R) subtotal from page 2 |  |  |  |  | 0 |  | 0
| REUSED TOTAL (R) |  |  |  |  | 0 |  | 0 |  | REUSED TOTAL (R) |  |  |  |  | 0 |  | 0 |  | REUSED TOTAL (R) |  |  |  |  | 0 |  | 0 |  | REUSED TOTAL (R) |  |  |  |  | 0 |  | 0 |  | REUSED TOTAL (R) |  |  |  |  | 0 |  | 0 |  | REUSED TOTAL (R) |  |  |  |  | 0 |  | 0 |  | REUSED TOTAL (R) |  |  |  |  | 0 |  | 0
[6 empty] | Size |  | Time | [6 empty] | Size |  | Time | [6 empty] | Size |  | Time | [6 empty] | Size |  | Time | [6 empty] | Size |  | Time | [6 empty] | Size |  | Time | [6 empty] | Size |  | Time
| Estimated Object LOC: |  |  | E = BA+NO+M |  | 0 |  |  |  | Estimated Object LOC: |  |  | E = BA+NO+M |  | 0 |  |  |  | Estimated Object LOC: |  |  | E = BA+NO+M |  | 0 |  |  |  | Estimated Object LOC: |  |  | E = BA+NO+M |  | 0 |  |  |  | Estimated Object LOC: |  |  | E = BA+NO+M |  | 0 |  |  |  | Estimated Object LOC: |  |  | E = BA+NO+M |  | 0 |  |  |  | Estimated Object LOC: |  |  | E = BA+NO+M |  | 0
| Regression Parameter: |  |  | B0 |  | 0 |  | 0 |  | Regression Parameter: |  |  | B0 |  | 0 |  | 0 |  | Regression Parameter: |  |  | B0 |  | 0 |  | 0 |  | Regression Parameter: |  |  | B0 |  | 0 |  | 0 |  | Regression Parameter: |  |  | B0 |  | 0 |  | 0 |  | Regression Parameter: |  |  | B0 |  | 0 |  | 0 |  | Regression Parameter: |  |  | B0 |  | 0 |  | 0
| Regression Parameter: |  |  | B1 |  | 0 |  | 0 |  | Regression Parameter: |  |  | B1 |  | 0 |  | 0 |  | Regression Parameter: |  |  | B1 |  | 0 |  | 0 |  | Regression Parameter: |  |  | B1 |  | 0 |  | 0 |  | Regression Parameter: |  |  | B1 |  | 0 |  | 0 |  | Regression Parameter: |  |  | B1 |  | 0 |  | 0 |  | Regression Parameter: |  |  | B1 |  | 0 |  | 0
| Estimated New and Changed LOC: |  |  | N = B0 + B1` * E |  | 0 |  |  |  | Estimated New and Changed LOC: |  |  | N = B0 + B1` * E |  | 0 |  |  |  | Estimated New and Changed LOC: |  |  | N = B0 + B1` * E |  | 0 |  |  |  | Estimated New and Changed LOC: |  |  | N = B0 + B1` * E |  | 0 |  |  |  | Estimated New and Changed LOC: |  |  | N = B0 + B1` * E |  | 0 |  |  |  | Estimated New and Changed LOC: |  |  | N = B0 + B1` * E |  | 0 |  |  |  | Estimated New and Changed LOC: |  |  | N = B0 + B1` * E |  | 0
| Estimated Total LOC: |  |  | T = N + B - D - M + R |  | 0 |  |  |  | Estimated Total LOC: |  |  | T = N + B - D - M + R |  | 0 |  |  |  | Estimated Total LOC: |  |  | T = N + B - D - M + R |  | 0 |  |  |  | Estimated Total LOC: |  |  | T = N + B - D - M + R |  | 0 |  |  |  | Estimated Total LOC: |  |  | T = N + B - D - M + R |  | 0 |  |  |  | Estimated Total LOC: |  |  | T = N + B - D - M + R |  | 0 |  |  |  | Estimated Total LOC: |  |  | T = N + B - D - M + R |  | 0
| Estimated Total New Reuse (sum of * LOC): |  |  |  |  | 0 |  |  |  | Estimated Total New Reuse (sum of * LOC): |  |  |  |  | 0 |  |  |  | Estimated Total New Reuse (sum of * LOC): |  |  |  |  | 0 |  |  |  | Estimated Total New Reuse (sum of * LOC): |  |  |  |  | 0 |  |  |  | Estimated Total New Reuse (sum of * LOC): |  |  |  |  | 0 |  |  |  | Estimated Total New Reuse (sum of * LOC): |  |  |  |  | 0 |  |  |  | Estimated Total New Reuse (sum of * LOC): |  |  |  |  | 0
| Estimated Total Developent Time: |  |  | Time = B0 + B1` * E |  |  |  | 0 |  | Estimated Total Developent Time: |  |  | Time = B0 + B1` * E |  |  |  | 0 |  | Estimated Total Developent Time: |  |  | Time = B0 + B1` * E |  |  |  | 0 |  | Estimated Total Developent Time: |  |  | Time = B0 + B1` * E |  |  |  | 0 |  | Estimated Total Developent Time: |  |  | Time = B0 + B1` * E |  |  |  | 0 |  | Estimated Total Developent Time: |  |  | Time = B0 + B1` * E |  |  |  | 0 |  | Estimated Total Developent Time: |  |  | Time = B0 + B1` * E |  |  |  | 0
| Prediction Range: |  |  | Range |  | 0 |  | 0 |  | Prediction Range: |  |  | Range |  | 0 |  | 0 |  | Prediction Range: |  |  | Range |  | 0 |  | 0 |  | Prediction Range: |  |  | Range |  | 0 |  | 0 |  | Prediction Range: |  |  | Range |  | 0 |  | 0 |  | Prediction Range: |  |  | Range |  | 0 |  | 0 |  | Prediction Range: |  |  | Range |  | 0 |  | 0
| Upper Prediction Interval: |  |  | UPI = N + Range | [5 empty] | Upper Prediction Interval: |  |  | UPI = N + Range | [5 empty] | Upper Prediction Interval: |  |  | UPI = N + Range | [5 empty] | Upper Prediction Interval: |  |  | UPI = N + Range | [5 empty] | Upper Prediction Interval: |  |  | UPI = N + Range | [5 empty] | Upper Prediction Interval: |  |  | UPI = N + Range | [5 empty] | Upper Prediction Interval: |  |  | UPI = N + Range
| Lower Prediction Interval: |  |  | LPI = N - Range | [5 empty] | Lower Prediction Interval: |  |  | LPI = N - Range | [5 empty] | Lower Prediction Interval: |  |  | LPI = N - Range | [5 empty] | Lower Prediction Interval: |  |  | LPI = N - Range | [5 empty] | Lower Prediction Interval: |  |  | LPI = N - Range | [5 empty] | Lower Prediction Interval: |  |  | LPI = N - Range | [5 empty] | Lower Prediction Interval: |  |  | LPI = N - Range
| Prediction Interval Percent |  |  |  |  | 70% |  | 70% |  | Prediction Interval Percent |  |  |  |  | 70% |  | 70% |  | Prediction Interval Percent |  |  |  |  | 70% |  | 70% |  | Prediction Interval Percent |  |  |  |  | 70% |  | 70% |  | Prediction Interval Percent |  |  |  |  | 70% |  | 70% |  | Prediction Interval Percent |  |  |  |  | 70% |  | 70% |  | Prediction Interval Percent |  |  |  |  | 70% |  | 70%
| Method Selected |  |  |  |  | 0 |  | 0 |  | Method Selected |  |  |  |  | 0 |  | 0 |  | Method Selected |  |  |  |  | 0 |  | 0 |  | Method Selected |  |  |  |  | 0 |  | 0 |  | Method Selected |  |  |  |  | 0 |  | 0 |  | Method Selected |  |  |  |  | 0 |  | 0 |  | Method Selected |  |  |  |  | 0 |  | 0
| R^2 |  |  |  |  | 0 |  | 0 |  | R^2 |  |  |  |  | 0 |  | 0 |  | R^2 |  |  |  |  | 0 |  | 0 |  | R^2 |  |  |  |  | 0 |  | 0 |  | R^2 |  |  |  |  | 0 |  | 0 |  | R^2 |  |  |  |  | 0 |  | 0 |  | R^2 |  |  |  |  | 0 |  | 0
| Size Estimating Template (continued) | [8 empty] | Size Estimating Template (continued) | [8 empty] | Size Estimating Template (continued) | [8 empty] | Size Estimating Template (continued) | [8 empty] | Size Estimating Template (continued) | [8 empty] | Size Estimating Template (continued) | [8 empty] | Size Estimating Template (continued)
| Student | 0 |  |  |  | Date |  | ????? |  | Student | 0 |  |  |  | Date |  | ????? |  | Student | 0 |  |  |  | Date |  | ????? |  | Student | 0 |  |  |  | Date |  | ????? |  | Student | 0 |  |  |  | Date |  | ????? |  | Student | 0 |  |  |  | Date |  | ????? |  | Student | 0 |  |  |  | Date |  | ?????
| Instructor | 0 |  |  |  | Program# |  | 3A |  | Instructor | 0 |  |  |  | Program# |  | 4A |  | Instructor | 0 |  |  |  | Program# |  | 5A |  | Instructor | 0 |  |  |  | Program# |  | 6A |  | Instructor | 0 |  |  |  | Program# |  | 7A |  | Instructor | 0 |  |  |  | Program# |  | 8A |  | Instructor | 0 |  |  |  | Program# |  | 10A
| OBJECT LOC |  |  |  |  | ESTIMATE |  | ACTUAL |  | OBJECT LOC |  |  |  |  | ESTIMATE |  | ACTUAL |  | OBJECT LOC |  |  |  |  | ESTIMATE |  | ACTUAL |  | OBJECT LOC |  |  |  |  | ESTIMATE |  | ACTUAL |  | OBJECT LOC |  |  |  |  | ESTIMATE |  | ACTUAL |  | OBJECT LOC |  |  |  |  | ESTIMATE |  | ACTUAL |  | OBJECT LOC |  |  |  |  | ESTIMATE |  | ACTUAL
| BASE ADDITIONS: |  | TYPE | METHODS | REL. SIZE | LOC |  | LOC |  | BASE ADDITIONS: |  | TYPE | METHODS | REL. SIZE | LOC |  | LOC |  | BASE ADDITIONS: |  | TYPE | METHODS | REL. SIZE | LOC |  | LOC |  | BASE ADDITIONS: |  | TYPE | METHODS | REL. SIZE | LOC |  | LOC |  | BASE ADDITIONS: |  | TYPE | METHODS | REL. SIZE | LOC |  | LOC |  | BASE ADDITIONS: |  | TYPE | METHODS | REL. SIZE | LOC |  | LOC |  | BASE ADDITIONS: |  | TYPE | METHODS | REL. SIZE | LOC |  | LOC
C++ Object Size in LOC per Method
[64 empty] | Category | VS | S | M | L | VL
[64 empty] | Calc | 2.34 | 5.13 | 11.25 | 24.66 | 54.04
[64 empty] | Data | 2.6 | 4.79 | 8.84 | 16.31 | 30.09
[64 empty] | I/O | 9.01 | 12.06 | 16.15 | 21.62 | 28.93
[64 empty] | Logic | 7.55 | 10.98 | 15.98 | 23.25 | 33.83
[64 empty] | Set-up | 3.88 | 5.04 | 6.56 | 8.53 | 11.09
[64 empty] | Text | 3.75 | 8 | 17.07 | 36.41 | 77.66
| SUBTOTAL BASE ADDITIONS (BA) => |  |  |  |  | 0 |  | 0 |  | SUBTOTAL BASE ADDITIONS (BA) => |  |  |  |  | 0 |  | 0 |  | SUBTOTAL BASE ADDITIONS (BA) => |  |  |  |  | 0 |  | 0 |  | SUBTOTAL BASE ADDITIONS (BA) => |  |  |  |  | 0 |  | 0 |  | SUBTOTAL BASE ADDITIONS (BA) => |  |  |  |  | 0 |  | 0 |  | SUBTOTAL BASE ADDITIONS (BA) => |  |  |  |  | 0 |  | 0 |  | SUBTOTAL BASE ADDITIONS (BA) => |  |  |  |  | 0 |  | 0
| NEW OBJECTS: |  | TYPE | METHODS | REL. SIZE | LOC | * | LOC | * | NEW OBJECTS: |  | TYPE | METHODS | REL. SIZE | LOC | * | LOC | * | NEW OBJECTS: |  | TYPE | METHODS | REL. SIZE | LOC | * | LOC | * | NEW OBJECTS: |  | TYPE | METHODS | REL. SIZE | LOC | * | LOC | * | NEW OBJECTS: |  | TYPE | METHODS | REL. SIZE | LOC | * | LOC | * | NEW OBJECTS: |  | TYPE | METHODS | REL. SIZE | LOC | * | LOC | * | NEW OBJECTS: |  | TYPE | METHODS | REL. SIZE | LOC | * | LOC | *
| SUBTOTAL NEW OBJECTS (NO) => |  |  |  |  | 0 |  | 0 |  | SUBTOTAL NEW OBJECTS (NO) => |  |  |  |  | 0 |  | 0 |  | SUBTOTAL NEW OBJECTS (NO) => |  |  |  |  | 0 |  | 0 |  | SUBTOTAL NEW OBJECTS (NO) => |  |  |  |  | 0 |  | 0 |  | SUBTOTAL NEW OBJECTS (NO) => |  |  |  |  | 0 |  | 0 |  | SUBTOTAL NEW OBJECTS (NO) => |  |  |  |  | 0 |  | 0 |  | SUBTOTAL NEW OBJECTS (NO) => |  |  |  |  | 0 |  | 0
| REUSED OBJECTS |  |  |  |  | LOC |  | LOC |  | REUSED OBJECTS |  |  |  |  | LOC |  | LOC |  | REUSED OBJECTS |  |  |  |  | LOC |  | LOC |  | REUSED OBJECTS |  |  |  |  | LOC |  | LOC |  | REUSED OBJECTS |  |  |  |  | LOC |  | LOC |  | REUSED OBJECTS |  |  |  |  | LOC |  | LOC |  | REUSED OBJECTS |  |  |  |  | LOC |  | LOC
| SUBTOTAL REUSED (R) => |  |  |  |  | 0 |  | 0 |  | SUBTOTAL REUSED (R) => |  |  |  |  | 0 |  | 0 |  | SUBTOTAL REUSED (R) => |  |  |  |  | 0 |  | 0 |  | SUBTOTAL REUSED (R) => |  |  |  |  | 0 |  | 0 |  | SUBTOTAL REUSED (R) => |  |  |  |  | 0 |  | 0 |  | SUBTOTAL REUSED (R) => |  |  |  |  | 0 |  | 0 |  | SUBTOTAL REUSED (R) => |  |  |  |  | 0 |  | 0
Project

## PROBE
PROBE Method Selector |  | PROBE Method Calculations | [8 empty] | Historical Data | [5 empty] | Regression Data
Project | 1 | PROBE Method | A |  | B |  | C |  | D |  | Prog | Est. (N&C) | Actual (N&C) | Actual Min. | Est. (E) | Outliers | Item | Est. (E) Xi | Act. (N) Yi | Act. Min. Yi | Est. (N) Xi | Act. (N) Yi | Act. Min. Yi
Estimate (E) | 0 |  | Size | Time | Size | Time | Size | Time | Size | Time | 1 |  | 0 |  |  |  | 1 | [6 empty] | ESTIMATION RESULTS
Size Method | 4 | Estimate | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 0 |  | 2 | 0 | 0 |  |  |  | 2 | [6 empty] | SIZE | [5 empty] | TIME
Selector |  | R-Squared | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  |  |  |  | 3 | 0 | 0 |  | 0 |  | 3 | [6 empty] | M | E | R | B0 | B1 | R2 | M | E | R | B0 | B1 | R2
Size Estimate | 0 | Beta0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0 |  | 4
Range | 0 | Beta1 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 1 | #DIV/0! | 5 | 0 | 0 |  | 0 |  | 5
B0 | 0 | Range (70%) | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  |  | 6 | 0 | 0 |  | 0 |  | 6
B1 | 1 | UPI | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  |  |  |  | 7 | 0 | 0 |  | 0 |  | 7
R^2 | 0 | LPI | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  |  |  |  | 8 | 0 | 0 |  | 0 |  | 8
Time Method | 4 | Variance | #NAME? | #NAME? | #NAME? | #NAME? | [10 empty] | 9
Selector |  | Std. Deviation | #NAME? | #NAME? | #NAME? | #NAME?
Time Estimate | 0
Range | 0
B0 | 0
B1 | #DIV/0!
R^2 | 0
Transfer Estimate to Size Estimating Template

## PROBE.XLM (hidden)
Names | Formulas | Comments | Copyright 1996 James W. Over
| LRVariance | knownYs, knownXs, betaO, beta1
#NAME?
#NAME?
#NAME?
#NAME?
#NAME?
LRVSum | 0
#NAME?
LRVy | #VALUE!
LRVx | #VALUE!
#NAME?
#NAME?
#NAME?
#NAME?
| PredictionRange | known Ys, known Xs, beta0, beta1, Xk, prcnt
#NAME?
#NAME?
| #NAME? | Copyright 1996 James W. Over
#NAME?
#NAME?
#NAME?
#NAME?
LRPRVar | #NAME?
LRPRStd | #NAME?
LRPRt | #VALUE!
LRPRXavg | #N/A
LRPRVSum | 0
#NAME?
LRPRVx | #VALUE!
#NAME?
#NAME?
#NAME?
#NAME?

## TimeLog
Project | Phase | Date | Start | Int. | Stop | Delta | Comments

## DefectLog
Project | Date | Num | Type | Injected | Removed | FixTime | Fix Ref. | Description

## R3
Defect Densities |  |  |  | Compile and Test Defects
Program Number | New and Changed LOC | Total Defects | Defects per KLOC | Defects found in compile | Compile defects per KLOC | Defects found in test | Test defects per KLOC
1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Totals | 0 | 0 | 0 | 0 | 0 | 0 | 0
Defect Fix Times
|  | Defects found in compiling | Defects found in testing | Total defects found
Defects | Tot. fix time | 0 | 0 | #VALUE!
injected in | Tot. defects | 0 | 0 | #VALUE!
designing | Avg. fix time | 0 | 0 | #VALUE!
Defects | Tot. fix time | 0 | 0 | #VALUE!
injected in | Tot. defects | 0 | 0 | #VALUE!
coding | Avg. fix time | 0 | 0 | #VALUE!
Total | Tot. fix time | #VALUE! | #VALUE! | #VALUE!
defects | Tot. defects | #VALUE! | #VALUE! | #VALUE!
injected | Avg. fix time | #VALUE! | #VALUE! | #VALUE!
Database criteria for defect fix times |  |  |  | Criteria for-> | injected in... | found in...
Injected | Removed | fixtime | total |  | design | compile
DLD | COMPILE | 0 | 0
Injected | Removed | fixtime | total |  | design | test
DLD | TEST | 0 | 0
Injected |  | fixtime | total |  | design | anywhere
DLD |  | #VALUE! | #VALUE!
Injected | Removed | fixtime | total |  | coding | compile
CODE | COMPILE | 0 | 0
Injected | Removed | fixtime | total |  | coding | test
CODE | TEST | 0 | 0
Injected |  | fixtime | total |  | coding | anywhere
CODE |  | #VALUE! | #VALUE!
| Removed | fixtime | total |  | anywhere | complie
| COMPILE | #VALUE! | #VALUE!
| Removed | fixtime | total |  | anywhere | test
| TEST | #VALUE! | #VALUE!
|  | fixtime | total |  | anywhere | anywhere
|  | #VALUE! | #VALUE!

## R4
Table D23
| Number Injected |  | Percentage Injected |  | Number Removed |  | Percentage Removed
Type | Design | Code | Design | Code | Compile | Test | Compile | Test
10 | 0 | 0 | 0% | 0% | 0 | 0 | 0% | 0%
20 | 0 | 0 | 0% | 0% | 0 | 0 | 0% | 0%
30 | 0 | 0 | 0% | 0% | 0 | 0 | 0% | 0%
40 | 0 | 0 | 0% | 0% | 0 | 0 | 0% | 0%
50 | 0 | 0 | 0% | 0% | 0 | 0 | 0% | 0%
60 | 0 | 0 | 0% | 0% | 0 | 0 | 0% | 0%
70 | 0 | 0 | 0% | 0% | 0 | 0 | 0% | 0%
80 | 0 | 0 | 0% | 0% | 0 | 0 | 0% | 0%
90 | 0 | 0 | 0% | 0% | 0 | 0 | 0% | 0%
100 | 0 | 0 | 0% | 0% | 0 | 0 | 0% | 0%
Total | 0 | 0 |  |  | 0 | 0
Table D24
Defect Type |  | Number of defects through Compile |  | Number of defects found in Compile |  | Percentage of Type found by the Compiler
10 |  | 0 |  | 0
20 |  | 0 |  | 0
30 |  | 0 |  | 0
40 |  | 0 |  | 0
50 |  | 0 |  | 0
60 |  | 0 |  | 0
70 |  | 0 |  | 0
80 |  | 0 |  | 0
90 |  | 0 |  | 0
100 |  | 0 |  | 0
Total |  | 0 |  | 0
Injected Criteria |  |  |  |  | Removed Criteria |  |  |  | Injected/Removed Criteria
Injected | Type | Injected |  |  | Removed | Type | Removed |  | Injected | Type | Removed
DLD | 10 | CODE |  |  | COMPILE | 10 | TEST |  | PLAN | 10 | PLAN
Injected | Type | Injected |  |  | Removed | Type | Removed |  | DLD | 10 | DLD
DLD | 20 | CODE |  |  | COMPILE | 20 | TEST |  | DLDR | 10 | DLDR
Injected | Type | Injected |  |  | Removed | Type | Removed |  | CODE | 10 | CODE
DLD | 30 | CODE |  |  | COMPILE | 30 | TEST |  | CR | 10 | CR
Injected | Type | Injected |  |  | Removed | Type | Removed |  | COMPILE | 10 | COMPILE
DLD | 40 | CODE |  |  | COMPILE | 40 | TEST |  | Injected | Type | Removed
Injected | Type | Injected |  |  | Removed | Type | Removed |  | PLAN | 20 | PLAN
DLD | 50 | CODE |  |  | COMPILE | 50 | TEST |  | DLD | 20 | DLD
Injected | Type | Injected |  |  | Removed | Type | Removed |  | DLDR | 20 | DLDR
DLD | 60 | CODE |  |  | COMPILE | 60 | TEST |  | CODE | 20 | CODE
Injected | Type | Injected |  |  | Removed | Type | Removed |  | CR | 20 | CR
DLD | 70 | CODE |  |  | COMPILE | 70 | TEST |  | COMPILE | 20 | COMPILE
Injected | Type | Injected |  |  | Removed | Type | Removed |  | Injected | Type | Removed
DLD | 80 | CODE |  |  | COMPILE | 80 | TEST |  | PLAN | 30 | PLAN
Injected | Type | Injected |  |  | Removed | Type | Removed |  | DLD | 30 | DLD
DLD | 90 | CODE |  |  | COMPILE | 90 | TEST |  | DLDR | 30 | DLDR
Injected | Type | Injected |  |  | Removed | Type | Removed |  | CODE | 30 | CODE
DLD | 100 | CODE |  |  | COMPILE | 100 | TEST |  | CR | 30 | CR
[9 empty] | COMPILE | 30 | COMPILE
[9 empty] | Injected | Type | Removed
[9 empty] | PLAN | 40 | PLAN
[9 empty] | DLD | 40 | DLD
[9 empty] | DLDR | 40 | DLDR
[9 empty] | CODE | 40 | CODE
[9 empty] | CR | 40 | CR
[9 empty] | COMPILE | 40 | COMPILE
[9 empty] | Injected | Type | Removed
[9 empty] | PLAN | 50 | PLAN
[9 empty] | DLD | 50 | DLD
[9 empty] | DLDR | 50 | DLDR
[9 empty] | CODE | 50 | CODE
[9 empty] | CR | 50 | CR
[9 empty] | COMPILE | 50 | COMPILE
[9 empty] | Injected | Type | Removed
[9 empty] | PLAN | 60 | PLAN
[9 empty] | DLD | 60 | DLD
[9 empty] | DLDR | 60 | DLDR
[9 empty] | CODE | 60 | CODE
[9 empty] | CR | 60 | CR
[9 empty] | COMPILE | 60 | COMPILE
[9 empty] | Injected | Type | Removed
[9 empty] | PLAN | 70 | PLAN
[9 empty] | DLD | 70 | DLD
[9 empty] | DLDR | 70 | DLDR
[9 empty] | CODE | 70 | CODE
[9 empty] | CR | 70 | CR
[9 empty] | COMPILE | 70 | COMPILE
[9 empty] | Injected | Type | Removed
[9 empty] | PLAN | 80 | PLAN
[9 empty] | DLD | 80 | DLD
[9 empty] | DLDR | 80 | DLDR
[9 empty] | CODE | 80 | CODE
[9 empty] | CR | 80 | CR
[9 empty] | COMPILE | 80 | COMPILE
[9 empty] | Injected | Type | Removed
[9 empty] | PLAN | 90 | PLAN
[9 empty] | DLD | 90 | DLD
[9 empty] | DLDR | 90 | DLDR
[9 empty] | CODE | 90 | CODE
[9 empty] | CR | 90 | CR
[9 empty] | COMPILE | 90 | COMPILE
[9 empty] | Injected | Type | Removed
[9 empty] | PLAN | 100 | PLAN
[9 empty] | DLD | 100 | DLD
[9 empty] | DLDR | 100 | DLDR
[9 empty] | CODE | 100 | CODE
[9 empty] | CR | 100 | CR
[9 empty] | COMPILE | 100 | COMPILE

## Pareto
10 | 0 | 10 | 0
20 | 0 | 20 | 0
30 | 0 | 30 | 0
40 | 0 | 40 | 0
50 | 0 | 50 | 0
60 | 0 | 60 | 0
70 | 0 | 70 | 0
80 | 0 | 80 | 0
90 | 0 | 90 | 0
100 | 0 | 100 | 0

## DefectAnalysis
Analysis of the defect data for the programs you have written to date.
Total defects per KLOC
Defects per KLOC injected in design and code
Defects per KLOC removed in design review, code review, compile, and test
Defect % distribution by phase, injected and removed
x-y plot of compile vs. test defects
A copy of selected portions of your development data, as entered in your Summary file.
Item: | EstLOC | ActLOC | EstMin | ActMin | EstDef | ActDef | Time by Phase | [7 empty] | Defects Injected by Phase | [6 empty] | Defects Removed by Phase
[7 empty] | Planning | Design | Design | Code | Code | Compile | Test | PM | Planning | Design | Design | Code | Code | Compile | Test | Planning | Design | Design | Code | Code | Compile | Test
[9 empty] | Review |  | Review | [5 empty] | Review |  | Review |  |  |  |  | Review |  | Review
Formulas
1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Totals | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Analysis calculations
| Total Def |  | Def. Inj. in Design |  | Def. inj. in Code |  | Def. rem. in Des. Rev. |  | Def. rem. in CodeRev. |  | DefRemComp |  | DefRemTest
| Def/KLOC |  | Def/KLOC |  | Def/KLOC |  | Def/KLOC |  | Def/KLOC |  | Def/KLOC |  | Def/KLOC
Formulas | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
1 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
2 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
3 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
4 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
5 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
6 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
7 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
8 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
9 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
10 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Totals | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Defect Injection Distribution - % by phase
| Plng | Des | Design | DLDR | Des.Rev | Code | Code | CDR | CDR | Comp | Comp | Test | Test
|  |  | Cum. |  | Cum |  | Cum |  | Cum |  | Cum |  | Cum
Formulas | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Defect Removal Distribution - % by phase
| Planning | Design | Design | Des.Rev | Des.Rev | Code | Code | CDR | CDR | Comp | Comp | Test | Test
|  |  | Cum. |  | Cum |  | Cum |  | Cum |  | Cum |  | Cum
Formulas | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Totals | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## PlanAnalysis
Analysis of the time spent developing the programs to date
Size and size estimating error
Development time and time estimating error
Percent of development time spent in planning, postmortem, compile, and test
A copy of selected portions of your development data, as entered in your Summary file.
Item: | EstLoc | ActLoc | EstMin | ActLoc | EstDef | ActDef | Time by Phase | [7 empty] | Defects Injected by Phase | [6 empty] | Defects Removed by Phase
[7 empty] | Planning | Design | Design | Code | Code | Compile | Test | PM | Planning | Design | Design | Code | Code | Compile | Test | Planning | Design | Design | Code | Code | Compile | Test
[9 empty] | Review |  | Review | [5 empty] | Review |  | Review |  |  |  |  | Review |  | Review
Formulas
1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Totals | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Analysis calculations
| Size Error |  | Time |  | Time Error |  | Plan Time |  | PM Time |  | Plan+PM Time |  | Compile Time |  | Test Time |  | Compile+Test Time
| % |  | Hours |  | % |  | % |  | % |  | % |  | % |  | % |  | %
Formulas | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
1 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
2 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
3 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
4 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
5 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
6 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
7 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
8 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
9 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
10 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Totals | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0

## ProcessAnalysis
Analysis of the quality of the process used for the programs you have written to date.
Productivity
Comparative x-y plots of productivity, yield, A/FR, and test defects
A copy of selected portions of your development data, as entered in your Summary file.
Item: | EstLoc | ActLoc | EstMin | ActLoc | EstDef | ActDef | Time by Phase | [7 empty] | Defects Injected by Phase | [6 empty] | Defects Removed by Phase
[7 empty] | Planning | Design | Design | Code | Code | Compile | Test | PM | Planning | Design | Design | Code | Code | Compile | Test | Planning | Design | Design | Code | Code | Compile | Test
[9 empty] | Review |  | Review | [5 empty] | Review |  | Review |  |  |  |  | Review |  | Review
Formulas
1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Totals | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Analysis calculations
| Yield |  |  |  | Cost of Quality |  |  |  |  | DefRemTest |  | Productivity
| Early inj. | Early rem. | Yield% |  | Failure | Appraisal | TotalCOQ | A/FR |  | Def/KLOC |  | LOC/Hour
[5 empty] | Cost | Cost
Formulas | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0
1 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0
2 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0
3 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0
4 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0
5 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0
6 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0
7 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0
8 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0
9 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0
10 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0
Totals | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0

## QualityAnalysis
Analysis of the quality data for the programs you have written to date.
Yield
Cost of Quality
Appraisal to failure ratio (A/FR)
LOC reviewed per hour vs. yield
A copy of selected portions of your development data, as entered in your Summary file.
Item: | EstLoc | ActLoc | EstMin | ActLoc | EstDef | ActDef | Time by Phase | [7 empty] | Defects Injected by Phase | [6 empty] | Defects Removed by Phase
[7 empty] | Planning | Design | Design | Code | Code | Compile | Test | PM | Planning | Design | Design | Code | Code | Compile | Test | Planning | Design | Design | Code | Code | Compile | Test
[9 empty] | Review |  | Review | [5 empty] | Review |  | Review |  |  |  |  | Review |  | Review
Formulas
1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Totals | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Analysis calculations
| Yield |  |  |  | Cost of Quality |  |  |  |  | DefRemTest |  | LOC Reviewed/Hour |  |  |  | Review Yield
| Early inj. | Early rem. | Yield% |  | Failure | Appraisal | TotalCOQ | A/FR |  | Def/KLOC |  | DLDR | CDR | Both |  | DLDR | CDR
[5 empty] | Cost | Cost
Formulas | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0
1 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0
2 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0
3 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0
4 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0
5 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0
6 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0
7 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0
8 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0
9 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0
10 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0
Totals | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0

## SCMENUS (hidden)
Project | Assignment | Process | Processes | Phases | PSP0 | PSP0.1 | PSP1 | PSP1.1 | PSP2 | PSP2.1 | Type | Description | Object Type | Object Type | Relative Size | Method
1 | 1A | PSP0 | PSP0 | PLAN | PLAN | PLAN | PLAN | PLAN | PLAN | PLAN | 10 | Documentation | C | Calculation | VS | A
2 | 2A | PSP0.1 | PSP0.1 | DLD | DLD | DLD | DLD | DLD | DLD | DLD | 20 | Syntax | D | Data | S | B
3 | 3A | PSP1 | PSP1 | DLDR | CODE | CODE | CODE | CODE | DLDR | DLDR | 30 | Build, Package | IO | Input/Output | M | C
4 | 4A | PSP1.1 | PSP1.1 | CODE | COMPILE | COMPILE | COMPILE | COMPILE | CODE | CODE | 40 | Assignment | L | Logic | L | D
5 | 5A | PSP2 | PSP2 | CR | TEST | TEST | TEST | TEST | CR | CR | 50 | Interface | S | Set-up | VL
6 | 6A | PSP2.1 | PSP2.1 | COMPILE | PM | PM | PM | PM | COMPILE | COMPILE | 60 | Checking | T | Text
7 | 7A | PSP2.1 |  | TEST |  |  |  |  | TEST | TEST | 70 | Data
8 | 8A | PSP2.1 |  | PM |  |  |  |  | PM | PM | 80 | Function
[11 empty] | 90 | System
[11 empty] | 100 | Environment

## ProjDB (hidden)
Project | STU1 compatible |  | Time Summary |  | Defect Summary |  | Time by Phase | [19 empty] | Defects Injected by Phase | [19 empty] | Defects Removed by Phase | [19 empty] | Size | [17 empty] | Size Estimate |  | Time in Phase Est.
Number | Size N&C | [5 empty] | PLAN |  | HLD |  | HLDR |  | DLD |  | DLDR |  | CODE |  | CR |  | COMPILE |  | TEST |  | PM |  | PLAN |  | HLD |  | HLDR |  | DLD |  | DLDR |  | CODE |  | CR |  | COMPILE |  | TEST |  | PM |  | PLAN |  | HLD |  | HLDR |  | DLD |  | DLDR |  | CODE |  | CR |  | COMPILE |  | TEST |  | PM |  | Base |  | Deleted |  | Modified |  | Added |  | Reused |  | New and Changed |  | Total |  | Total New Reuse |  | Object LOC |  | Pred. Intervals |  | Pred. Intervals |  | Project
Item: | EstLoc | ActLOC | EstMin | ActMin | EstDef | ActDef | Est | Act | Est | Act | Est | Act | Est | Act | Est | Act | Est | Act | Est | Act | Est | Act | Est | Act | Est | Act | Est | Act | Est | Act | Est | Act | Est | Act | Est | Act | Est | Act | Est | Act | Est | Act | Est | Act | Est | Act | Est | Act | Est | Act | Est | Act | Est | Act | Est | Act | Est | Act | Est | Act | Est | Act | Est | Act | Est | Act | Est | Act | Est | Act | Est | Act | Est | Act | Est | Act | Est | Act | Est | Act | Est | Act | Est | Act | UPI | LPI | UPI | LPI | Date | Language
1 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
This worksheet holds the roll-up of actual time and defect data from the time log and defect log.
Worksheet pdb uses references to this worksheet for actual time in phase, defects injected in phase, and defects removed in phase.
Worksheet Summary uses references to worksheet pdb for actual data.
This worksheet holds the roll-up of actual time and defect data from the time log and defect log.

## pdb (hidden)
| Time in Phase | [9 empty] | Defects Injected | [9 empty] | Defects Removed
Program | Plan | HLD | HLDR | Design | DLDR | Code | CR | Compile | Test | PM | Plan | HLD | HLDR | Design | DLDR | Code | CR | Compile | Test | PM | Plan | HLD | HLDR | Design | DLDR | Code | CR | Compile | Test | PM
1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | 0 | [9 empty] | 0 | [9 empty] | 0
This worksheet references worksheet ProjDB to get actual time and defect data.
Worksheet Summary uses references to this worksheet for actual time in phase, defects injected in phase, and defects removed in phase.