# Assignment Kit for
Program 3

Personal Software Process (PSP) for Engineers: Part I

The Software Engineering Institute (SEI)

is a federally funded research and development center

sponsored by the U.S. Department of Defense and

operated by Carnegie Mellon University.

This material is approved for public release.

Distribution limited by the Software Engineering Institute to attendees.

Personal Software Process for Engineers: Part I

Assignment Kit for Program 3

Overview

| #### Overview | This assignment kit covers the following topics. |  |
| --- | --- | --- |
|  | Section | See Page |
|  | Prerequisites | 2 |
|  | Program 3 requirements | 3 |
|  | Regression overview | 5 |
|  | Using regression in the PSP | 6 |
|  | Calculating regression | 7 |
|  | A regression example | 8 |
|  | Assignment instructions | 10 |
|  | Guidelines and evaluation criteria | 17 |

| Prerequisites | Reading • Chapters 5 and 6 |
| --- | --- |

### Program 3 requirements

| Program 3 requirements | Using PSP1, write a program to • calculate the linear regression parameters β0and β1 for a set of n pairs of data, • given an estimate, xk calculate an improved prediction, yk where yk=β0+β1xk • enhance the linked list developed in program 1 to store the n data sets, where each record holds two real numbers Table 1 contains historical estimated and actual data for 10 programs. For program 11, the developer has estimated a proxy size of 386 LOC. Thoroughly test the program. At a minimum, run the following four test cases. • Test 1: Calculate the regression parameters between estimated proxy size and actual added and modified size in Table 1. Calculate plan added and modified size given an estimated proxy size of xk= 386. • Test 2: Calculate the regression parameters between estimated proxy size and actual development time in Table 1. Calculate time estimate given an estimated proxy size of xk= 386. • Test 3: Calculate the regression parameters between plan added and modified size and actual added and modified size in Table 1. Calculate plan added and modified size given an estimated proxy size of xk = 386. • Test 4: Calculate the regression parameters between plan added and modified size and actual development time in Table 1. Calculate time estimate given an estimated proxy size of xk = 386. Expected results are provided in Table 2. |
| --- | --- |

| Program Number | Estimated Proxy Size | Plan Added and Modified size | Actual Added and Modified Size | Actual Development Hours |
| --- | --- | --- | --- | --- |
| 1 | 130 | 163 | 186 | 15.0 |
| 2 | 650 | 765 | 699 | 69.9 |
| 3 | 99 | 141 | 132 | 6.5 |
| 4 | 150 | 166 | 272 | 22.4 |
| 5 | 128 | 137 | 291 | 28.4 |
| 6 | 302 | 355 | 331 | 65.9 |
| 7 | 95 | 136 | 199 | 19.4 |
| 8 | 945 | 1206 | 1890 | 198.7 |
| 9 | 368 | 433 | 788 | 38.8 |
| 10 | 961 | 1130 | 1601 | 138.2 |

Table 1

Continued on next page

### Program 3 requirements, Continued

| Expected results |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Test | Expected Value |  |  |  | Actual Value |  |  |  |
|  |  | β0 |  | β1 | yk | β0 | β1 | yk |  |
|  | Test 1 | -22.55 |  | 1.7279 | 644.429 |  |  |  |  |
|  | Test 2 | -4.039 |  | 0.1681 | 60.858 |  |  |  |  |
|  | Test 3 | -23.92 |  | 1.43097 | 528.4294 |  |  |  |  |
|  | Test 4 | -4.604 |  | 0.140164 | 49.4994 |  |  |  |  |

Table 2

Regression

| Overview | Linear regression is a way of optimally fitting a line to a set of data. The linear regression line is the line where the distance from all points to that line is minimized. The equation of a line can be written as y=β0+β1x In Figure 1, the best fit regression line has parameters of β0 = -4.0389 and β1 = 0.1681. y = -4.0389 +0.1681x 0 50 100 150 200 250 0 200 400 600 800 1000 1200 Estimated Proxy Size Actual Development Hours |
| --- | --- |

Figure 1

Continued on next page

Regression, Continued

| Using regression in the PSP | Looking at Figure 1, how many hours do you think it would take to develop a program with an estimated proxy size of 500? Using PROBE method A for time, the estimate would be TimeEstimate=β0+β1500 or an estimate of 80.011 hours. The PSP PROBE method uses regression parameters to make better predictions of size and time based on your historical data. PROBE methods A and B differ only in the historical data (x values) used to calculate the regression parameters. In PROBE method A, estimated proxy size are used as the x values. In PROBE method B, plan added and modified size are used as the x values. PROBE methods for size and time differ only in the historical data (y values) used to calculate the regression parameters. To predict improved size estimates, actual added and modified LOC are used as the y values. To predict time estimates, actual development times are used as the y values. |
| --- | --- |

| Historical Data Used |  | x values | y values |
| --- | --- | --- | --- |
| Size Estimating | PROBE A | Estimated Proxy Size | Actual Added and Modified Size |
|  | PROBE B | Plan Added and Modified Size | Actual Added and Modified Size |
| Time Estimating | PROBE A | Estimated Proxy Size | Actual Development Time |
|  | PROBE B | Plan Added and Modified Size | Actual Development Time |

Continued on next page

Regression, Continued

| Calculating regression | The formulas for calculating the regression parameters β0 and β1 are β1=i=1nxiyi−nxavgyavgi=1nxi2−nxavg2 β0=yavg−β1xavg where •  is the symbol for summation • i is an index to the n numbers • x and y are the two paired sets of data • n is the number of items in each set x and y • xavg is the average of the x values • yavg is the average of the y values |
| --- | --- |

A regression example

| #### A regression example | In this example, we will calculate the regression parameters (β0 and β1values) of the data in the Table 3. |
| --- | --- |

| n | x | y |
| --- | --- | --- |
| 1 | 130 | 186 |
| 2 | 650 | 699 |
| 3 | 99 | 132 |
| 4 | 150 | 272 |
| 5 | 128 | 291 |
| 6 | 302 | 331 |
| 7 | 95 | 199 |
| 8 | 945 | 1890 |
| 9 | 368 | 788 |
| 10 | 961 | 1601 |

Table 3

β1=i=1nxiyi−nxavgyavgi=1nxi2−nxavg2

|  | - In this example there are 10 items in each dataset and therefore we set n = 10. - We can now solve the summation items in the regression formula. |
| --- | --- |

| n | x | y | x2 | x*y |
| --- | --- | --- | --- | --- |
| 1 | 130 | 186 | 16900 | 24180 |
| 2 | 650 | 699 | 422500 | 454350 |
| 3 | 99 | 132 | 9801 | 13068 |
| 4 | 150 | 272 | 22500 | 40800 |
| 5 | 128 | 291 | 16384 | 37248 |
| 6 | 302 | 331 | 91204 | 99962 |
| 7 | 95 | 199 | 9025 | 18905 |
| 8 | 945 | 1890 | 893025 | 1786050 |
| 9 | 368 | 788 | 135424 | 289984 |
| 10 | 961 | 1601 | 923521 | 1538561 |
| Total | i=110xi=3828 | i=110yi=6389 | i=110xi2=2540284 | i=110xiyi=4303108 |
|  | xavg=382810=382.8 | yavg=638910=638.9 |  |  |

Continued on next page

A regression example, Continued

| #### A correlation example, cont. | - We can then substitute the values into the formula β1=4303108−10∗382.8∗638.92540284−10∗382.82 β1=18573991074926=1.727932 - We can then substitute the values in the β0 formula β0=yavg−β1xavg β0=638.9−1.727932∗382.8=−22.5525 - We now find yk from the formula yk=β0+β1xk yk=−22.5525+1.727932∗386=644.4294 |
| --- | --- |

### Assignment instructions

| #### Assignment instructions | Before starting program 3, review the top-level PSP1 process script below to ensure that you understand the “big picture” before you begin. Also, ensure that you have all of the required inputs before you begin the planning phase. |
| --- | --- |

PSP1 Process Script

| Purpose | - To guide the development of module-level programs |
| --- | --- |
| Entry Criteria | - Problem description - PSP1 Project Plan Summary form - Size Estimating template - Historical size and time data (estimated and actual) - Time and Defect Recording logs - Defect Type, Coding, and Size Measurement standards - Stopwatch (optional) |

| Step | Activities | Description |
| --- | --- | --- |
| 1 | Planning | - Produce or obtain a requirements statement. - Use the PROBE method to estimate the added and modified size of this program. - Complete the Size Estimating template. - Use the PROBE method to estimate the required development time. - Enter the plan data in the Project Plan Summary form. - Complete the Time Recording log. |
| 2 | Development | - Design the program. - Implement the design. - Compile the program, and fix and log all defects found. - Test the program, and fix and log all defects found. - Complete the Time Recording log. |
| 3 | Postmortem | - Complete the Project Plan Summary form with actual time, defect, and size data. |

| Exit Criteria | - A thoroughly tested program - Completed Project Plan Summary form with estimated and actual data - Completed Size Estimating template - Completed Test Report template - Completed PIP forms - Completed Time and Defect Recording logs |
| --- | --- |

Continued on next page

Assignment instructions, Continued

| #### Planning phase | Plan program 3 following the PSP1 planning phase and the PROBE estimating scripts. |
| --- | --- |

PSP1 Planning Script

| Purpose | - To guide the PSP planning process |
| --- | --- |
| Entry Criteria | - Problem description - PSP1 Project Plan Summary form - Size Estimating template - Historical size and time data (estimated and actual) - Time Recording log |

| Step | Activities | Description |
| --- | --- | --- |
| 1 | Program Requirements | - Produce or obtain a requirements statement for the program. - Ensure that the requirements statement is clear and unambiguous. - Resolve any questions. |
| 2 | Size Estimate | - Produce a program conceptual design. - Use the PROBE method to estimate the added and modified size of this program. - Complete the Size Estimating template and Project Plan Summary form. |
| 3 | Resource Estimate | - Use the PROBE method to estimate the time required to develop this program. - Using the To Date % from the most recently developed program as a guide, distribute the development time over the planned project phases. |

| Exit Criteria | - Documented requirements statement - Program conceptual design - Completed Size Estimating template - Completed Project Plan Summary form with estimated program size and development time data - Completed Time Recording log |
| --- | --- |

|  | Verify that you have met all of the exit criteria for the planning phase, then have an instructor review your plan. After your plan has been reviewed, proceed to the development phase. |
| --- | --- |

Continued on next page

### Assignment instructions, Continued

|  | Use the PROBE method to create size and resource estimates. |
| --- | --- |

| Purpose | - To guide the size and time estimating process using the PROBE method |
| --- | --- |
| Entry Criteria | - Requirements statement - Size Estimating template and instructions - Size per item data for part types - Time Recording log - Historical size and time data |
| General | - This script assumes that you are using added and modified size data as the size-accounting types for making size and time estimates. - If you choose some other size-accounting types, replace every “added and modified” in this script with the size-accounting types of your choice. |

| Step | Activities | Description |
| --- | --- | --- |
| 1 | Conceptual Design | Review the requirements and produce a conceptual design. |
| 2 | Parts Additions | Follow the Size Estimating Template instructions to estimate the parts additions and the new reusable parts sizes. |
| 3 | Base Parts and Reused Parts | - For the base program, estimate the size of the base, deleted, modified, and added code. - Measure and/or estimate the side of the parts to be reused. |
| 4 | Size Estimating Procedure | - If you have sufficient estimated proxy size and actual added and modified size data (three or more points that correlate), use procedure 4A. - If you do not have sufficient estimated data but have sufficient plan added and modified and actual added and modified size data (three or more points that correlate), use procedure 4B. - If you have insufficient data or they do not correlate, use procedure 4C. - If you have no historical data, use procedure 4D. |
| 4A | Size Estimating Procedure 4A | - Using the linear-regression method, calculate theβ0and β1 parameters from the estimated proxy size and actual added and modified size data. - If the absolute value ofβ0is not near 0 (less than about 25% of the expected size of the new program), orβ1is not near 1.0 (between about 0.5 and 2.0), use procedure 4B. |
| 4B | Size Estimating Procedure 4B | - Using the linear-regression method, calculate theβ0andβ1parameters from the plan added and modified size and actual added and modified size data. - If the absolute value of β0is not near 0 (less than about 25% of the expected size of the new program), orβ1is not near 1.0 (between about 0.5 and 2.0), use procedure 4C. |
| 4C | Size Estimating Procedure 4C | If you have any data on plan added and modified size and actual added and modified size, setβ0= 0 and β1 = (actual total added and modified size to date/plan total added and modified size to date). |
| 4D | Size Estimating Procedure 4D | If you have no historical data, use your judgment to estimate added and modified size. |

(continued)

Continued on next page

### Assignment instructions, Continued

PROBE Estimating Script (Continued)

| Step | Activities | Description |
| --- | --- | --- |
| 5 | Time Estimating Procedure | - If you have sufficient estimated proxy size and actual development time data (three or more points that correlate), use procedure 5A. - If you do not have sufficient estimated size data but have sufficient plan added and modified size and actual development time data (three or more points that correlate), use procedure 5B. - If you have insufficient data or they do not correlate, use procedure 5C. - If you have no historical data, use procedure 5D. |
| 5A | Time Estimating Procedure 5A | - Using the linear-regression method, calculate theβ0andβ1 parameters from the estimated proxy size and actual total development time data. - Ifβ0is not near 0 (substantially smaller than the expected development time for the new program), orβ1is not within 50% of 1/(historical productivity), use procedure 5B. |
| 5B | Time Estimating Procedure 5B | - Using the linear-regression method, calculate theβ0andβ1 regression parameters from the plan added and modified size and actual total development time data. - Ifβ0is not near 0 (substantially smaller than the expected development time for the new program), orβ1is not within 50% of 1/(historical productivity), use procedure 5C. |
| 5C | Time Estimating Procedure 5C | - If you have data on estimated – added and modified size and actual development time, setβ0= 0 and β1 = (actual total development time to date/estimated – total added and modified size to date). - If you have data on plan – added and modified size and actual development time, setβ0= 0 and β1 = (actual total development time to date/plan total added and modified size to date). - If you only have actual time and size data, setβ0= 0 and β1 = (actual total development time to date/actual total added and modified size to date). |
| 5D | Time Estimating Procedure 5D | If you have no historical data, use your judgment to estimate the development time from the estimated added and modified size. |
| 6 | Time and Size Prediction Intervals | - If you used regression method A or B, calculate the 70% prediction intervals for the time and size estimates. - If you did not use the regression method or do not know how to calculate the prediction interval, calculate the minimum and maximum development time estimate limits from your historical maximum and minimum productivity for the programs written to date. |

| Exit Criteria | - Completed estimated and actual entries for all pertinent size categories - Completed PROBE Calculation Worksheet with size and time entries - Plan and actual values entered on the Project Plan Summary |
| --- | --- |

Continued on next page

Assignment instructions, Continued

| #### Development phase | Develop the program following the PSP1 development phase script. |
| --- | --- |

PSP1 Development Script

| Purpose | - To guide the development of small programs |
| --- | --- |
| Entry Criteria | - Requirements statement - Project Plan Summary form with estimated program size and development time - Time and Defect Recording logs - Defect Type standard and Coding standard |

| Step | Activities | Description |
| --- | --- | --- |
| 1 | Design | - Review the requirements and produce a design to meet them. - Record in the Defect Recording log any requirements defects found. - Record time in the Time Recording log. |
| 2 | Code | - Implement the design following the Coding standard. - Record in the Defect Recording log any requirements or design defects found. - Record time in the Time Recording log. |
| 3 | Compile | - Compile the program until there are no compile errors. - Fix all defects found. - Record defects in the Defect Recording log. - Record time in the Time Recording log. |
| 4 | Test | - Test until all tests run without error. - Fix all defects found. - Record defects in the Defect Recording log. - Record time in the Time Recording log. - Complete a Test Report template on the tests conducted and the results obtained. |

| Exit Criteria | - A thoroughly tested program that conforms to the Coding standard - Completed Test Report template - Completed Time and Defect Recording logs |
| --- | --- |

|  | Verify that you have met all of the exit criteria for the development phase, then proceed to the postmortem phase. |
| --- | --- |

Continued on next page

Assignment instructions, Continued

| #### Postmortem #### phase | Conduct the postmortem following the PSP1 postmortem script. |
| --- | --- |

PSP1 Postmortem Script

| Purpose | - To guide the PSP postmortem process |
| --- | --- |
| Entry Criteria | - Problem description and requirements statement - Project Plan Summary form with program size and development time data - Completed Test Report template - Completed Time and Defect Recording logs - A tested and running program that conforms to the coding and size measurement standards |

| Step | Activities | Description |
| --- | --- | --- |
| 1 | Defect Recording | - Review the Project Plan Summary to verify that all of the defects found in each phase were recorded. - Using your best recollection, record any omitted defects. |
| 2 | Defect Data Consistency | - Check that the data on every defect in the Defect Recording log are accurate and complete. - Verify that the numbers of defects injected and removed per phase are reasonable and correct. - Using your best recollection, correct any missing or incorrect defect data. |
| 3 | Size | - Count the size of the completed program. - Determine the size of the base, reused, deleted, modified, added, total, added and modified, and new reusable code. - Enter these data in the Project Plan Summary form. |
| 4 | Time | - Review the completed Time Recording log for errors or omissions. - Using your best recollection, correct any missing or incomplete time data. |

| Exit Criteria | - A thoroughly tested program that conforms to the coding and size measurement standards - Completed Test Report template - Completed Project Plan Summary form - Completed PIP forms describing process problems, improvement suggestions, and lessons learned - Completed Time and Defect Recording logs |
| --- | --- |

|  | Verify that you have met all of the exit criteria for the PSP1 postmortem phase, then submit your assignment. |
| --- | --- |

Continued on next page

Assignment instructions, Continued

| #### Submitting your assignment | When you’ve completed the postmortem phase, submit your assignment package, source code, and test results to the instructor. The order for the assignment package is • PSP1 Project Plan Summary form • Test Report template • PIP form • Size Estimating template • PROBE Calculation worksheet • Time Recording log • Defect Recording log • source program listing • test results |
| --- | --- |

### Guidelines and evaluation criteria for program 3

| #### Evaluation criteria | Your process report must be • complete • legible • in the specified order | Your process data must be • accurate • precise • self-consistent |
| --- | --- | --- |

| #### Suggestions | Remember, you should complete this assignment today. Keep your programs simple. You will learn as much from developing small programs as from large ones. If you are not sure about something, ask your instructor for clarification. Software is not a solo business, so you do not have to work alone. - You must, however, produce your own estimates, designs, code, and completed forms and reports. - You may have others review your work, and you may change it as a result. - You should note any help you receive from others in your process report. Log the review time that you and your associates spend, and log the defects found or any changes made. |
| --- | --- |